Republika e Kosovës

Republika Kosova - Republic of Kosovo

Qeveria – Vlada - Government

Zyra e Kryeministrit / Kancelarija Premijera / Office of the Prime Minister

Sekretariati Koordinues i Qeverisë / Koordinacioni Sekretariat Vlade / Government Coordination Secretariat

DRAFT- Plan of Public Meetings for Preparation of Concept-Document for Public Procurement

Prishtina, 2019

| Activity | Information on the activity | People in charge of the activity | Timeframe |
| --- | --- | --- | --- |
| Organizing a Public meeting | - The public meeting is a requirement according to the Guidelines for compiling CPs, which is organized with the aim of discussing the main issues and topics that should be included in the CP analysis. | Communication Official- Group Coordinator | 26th April 2019 |
| Sending the document for preliminary Consultation in accordance with Article 7 of GRP | Upon completion of the first draft, the document is sent for preliminary consultation as set out in the Government's Rules of Procedures - Article 7 - MoF/PPRC will summarize all parts of the concept paper and take care of the translation and procedures needed for this stage | Leader of the Working group, Group’s Coordinator | 20th June 2019 (15 work days) |
| Sending the document for public consultation | According to the Rules of Procedure and the Regulation of Minimum Standards for Consultation, the document should be published on the online platform for public discussion - MoF will compile the concept document and take care of the necessary procedures for this stage | Leader of the Working group | 22th July 2019 |
| Consulatative meetings with stakeholders | - Consultative meeting with CSOs’ representatives - Consultative meeting with business associations representatives - Consultative meeting with representatives from international organizations present in Kosovo | Working group, Working group, Working group, | 24 th July 2019 25th July 2019 26t h July 2019 |